ACTIONS AND DEADLINES

Team Dart — Actions and Deadlines

From Admin Meeting 4, Thursday 29 October 2026

Draft for correction. The short list the team asked for; detail is in the Admin Meeting 4 summary. “Not set” means no date was agreed.

# Actions

| Due | Owner | Action |
| --- | --- | --- |
| Fri 30 Oct | Each slide owner | Put slide content and notes in the pipeline Word document. Slides: Mmenyene 1–3, Adekunle 4–5, Warren 6–7, Anne-Marie 8, Fuyang 9–10. |
| ASAP; before Mon 2 Nov | Each session’s note-taker | Complete the observation form and notes; upload them to the SharePoint folder. |
| Sun 1 Nov; latest 8:00 am Mon 2 Nov | Each member, for their own session | Fill in the Miro moderated-sessions table. Peggy: Fuyang · Angela: Mmenyene · Kai: Qiuchen · Bob: Warren · Cheryl: Anne-Marie · Carrie: Adekunle (names as transcribed). |
| Before Mon 2 Nov | Everyone | Look at the strategic product vision board and add material. |
| Mon 2 Nov | Anne-Marie | Synthesise the findings into the usability report; the Monday session reviews it. |
| Not set | Mmenyene; Warren | Remind Cohen of the client presentation booking and ask who is invited; Warren gives the names to faculty. |
| Not set (between 8 and 13 Nov) | Warren; Fuyang | Book the faculty dry run: Warren liaises with faculty; Fuyang coordinates the team calendar and invites. |
| Not set | Fuyang | Add 10, 12 and 13 Nov to the integrated plan and calendar. |
| 12 Nov (revisit about 5 Nov) | Not named | Capstone project description: draft, team review, Cohen’s approval, then to faculty. |
| After Session 18 is out | Adekunle; Fuyang | Plan the Milestone 2 retrospective together. |
| Not set | Adekunle | Create a Team folder for summaries and decision items and upload past ones; after each meeting, send and save a short actions-and-deadlines list. |

# Key dates

| Date | What |
| --- | --- |
| Fri 30 Oct; Sat 31 Oct | Slide content and notes due; Saturday session reviews pipeline and deck (corrections and polish only; Mmenyene leaves early) |
| Sun 1 Nov; Mon 2 Nov, 8:00 am | Session evidence in the Miro table; Monday working session reviews the report |
| Thu 5 Nov | Usability report due |
| Sun 8 Nov | Data pipeline due; strategic product vision due the 8th or 9th (to confirm) |
| Mon 9 Nov; Tue 10 Nov | Systems map (internal deadline, feeds the vision); MDPM 900 live session on Session 18 |
| Thu 12 Nov; Fri 13 Nov | Capstone project description due; client presentation (the 15th was also mentioned; to confirm) |

Unresolved: dry run date; briefing package before the client presentation; who builds the PowerPoint; decision log format.